## Change_Register_Enhanced
Document Title: | Change Management Register
Framework Reference: | SAMA CSF 3.3.7-4
Maintained By: | Information Security & DevOps
Last Updated: | 22-Feb-2026
Approval Status: | Approved by RCC
Change ID | Change Title | Change Type (Standard/Normal/Emergency) | Business Impact Assessment | Security Risk Level | Impact Assessment Completed (Y/N) | Security Testing Required (Y/N) | Penetration Testing Ref | Code Review Ref | SAST/SCA Ref | Business Owner Approval (Name/Date) | Cyber Security Approval (Name/Date) | CAB Approval (Meeting Ref/Date) | Environment Segregation Confirmed (Dev/Test/Prod) | Rollback Plan Reference | Emergency Change Indicator (Y/N) | Post-Implementation Review Completed (Y/N) | PIR Date | Status (Open/Implemented/Closed)
CR-2025-031 | Payments API Authentication Enhancement | Normal | No customer downtime expected | Medium | Y | Y | PT-2025-Q1-Ref12 | CRR-2025-031 | SNYK-Scan-#8891 | CPO - 10-Feb-2025 | Head of Security - 11-Feb-2025 | CAB-2025-02 - 12-Feb-2025 | Yes - Separate Dev/Test/Prod with RBAC | Rollback to v2.4.0 | N | Y | 14-Feb-2025 | Closed
CR-2025-045 | Database Patch - Critical CVE Fix | Emergency | Critical security remediation | High | Y | Y | PT-Not-Required | N/A | Nessus-Scan-#5562 | CPO - 03-Mar-2025 | Head of Security - 03-Mar-2025 | CAB-PostApproval-04-Mar-2025 | Yes - Segregated Infra Pipeline | Rollback to DB Snapshot 02-Mar-2025 | Y | Y | 05-Mar-2025 | Closed