## Cover
Prepared By | Head of Infosec
Last updated date | 27.02.2025
Approved By | CPO
Last approval date | 27.02.2025

## PM Risk Register
Risk Treatment Plan
ID | Project / Feature | Risks | Past incidents linked to the risk | Risk Owner | Identification Date (start date of the new feature going through Change and Release Management) | Type | Severity | Status | Implemented security controls | Security controls part of risk treatment plans (where applicable) | Control implementation status | Residual Risk | Risk status | Within Company Risk Appetite
1 | Report & HyperLink (Lean Open Banking) | Hyperlink misdirection exposing sensitive client data | No | Head of Product D&I - Alex | 31/01/2024 | Security | High | Mitigated | Validation between customer id , report id and lean app token should be in place so that one tpp can not fetch reports for someone else |  | Fully implemented | Low | Closed | Yes
2 | Report & HyperLink (Lean Open Banking) | Outdated links used by clients causing data discrepancy | No | Head of Product D&I - Alex | 31.01.2024 | Operational | Medium | Mitigated | Expiration of hyperlinks | Host validation should be in place for all new endpoints , if it is intended to be used on api host then other host should not be allowed to make request to those endpoints . | Fully implemented | Low | Closed | Yes
3 | Report & HyperLink (Lean Open Banking) | Unauthorized sharing of generated report URLs outside corporate domain | No | Head of Product D&I - Alex | 31.01.2024 | Security | High | Mitigated | RBAC SOC24x7 usecase to cover user invite | MFA on user login | Fully implemented | Low | Closed | Yes
4 | Report & HyperLink (Lean Open Banking) | Potential non-compliance with open banking regulations if reports show incorrect data | No | Chief Legal Officer | 31.01.2024 | Regulatory | Medium | Mitigated | Data consistency checks and IDOR checks | N/A | Fully implemented | Low | Closed | Yes
5 | Corporate Lending Insights | Inconsistent data feeds from multiple sources impacting decision accuracy | No | Head of Product D&I - Alex | 19.04.2024 | Data Integrity | Medium | Mitigated | Real-time validation and cross-source reconciliation Confidentiality requirements (Encryption in transit and encryption at rest, anonymization of sensitive data in logs) | N/A | Fully implemented | Low | Closed | Yes
6 | Corporate Lending Insights | Unauthorized data exposure in lending analytics dashboards Integrity requirement (Input validation) | No | Head of Product D&I - Alex | 19.04.2024 | Security | High | Mitigated | RBAC (Role-Based Access Control) and encryption at rest | Authentication & Authorization (role based access controls, least privilege, object level authorization) | Fully implemented | Low | Closed | Yes
7 | Corporate Lending Insights | Failure to meet corporate-lending compliance (e.g. cross-border rules) | No | Chief Legal Officer | 19.04.2024 | Regulatory | High | Mitigated | Regular compliance audits, legal sign-off for new markets | N/A | Fully implemented | Low | Closed | Yes
9 | Retail Insights for Lenders | Data privacy risk from storing consumer credit info | No | Chief Legal Officer | 09.09.2024 | Privacy | High | Mitigated | Encryption at rest, strict data retention policies | Host validation should be in place ( only api host should be able to make request to this endpoints ) | Fully implemented | Low | Closed | Yes
10 | Retail Insights for Lenders | Misinterpretation of retail credit scores leading to wrong offers | No | Head of Product D&I - Alex | 09.09.2024 | Business/Process | Medium | Mitigated | Scoring model validations and workflow approvals | Do not store PII data in any logs for this service such as Kibana | Fully implemented | Low | Closed | Yes
11 | Retail Insights for Lenders | Poor anonymization of transaction data used for analytics | No | Head of Product D&I - Alex | 09.09.2024 | Security | High | Mitigated | Tokenization, randomization of PII fields | Do not store PII data in any logs for this service such as Kibana | Fully implemented | Low | Closed | Yes
12 | Retail Insights for Lenders | Unexpected surge in queries slowing performance | No | Head of Product D&I - Alex | 09.09.2024 | Operational | Medium | Mitigated | Load balancing | Autoscaling | Fully implemented | Low | Closed | Yes
13 | AVS (IBAN Verification Service) | Third-party AVS API outage affecting onboarding flow | No | Head of Product D&I - Alex | 28.03.2024 | Vendor/3rd Party | High | Mitigated | SLA-based failover to secondary provider | Perform input validation for all headers and params | Fully implemented | Low | Closed | Yes
14 | AVS (IBAN Verification Service) | Inaccurate address data if provider database not updated | No | Head of Product D&I - Alex | 28.03.2024 | Data Integrity | Medium | Mitigated | Frequent syncs and periodic data quality checks | N/A | Fully implemented | Low | Closed | Yes
15 | AVS (IBAN Verification Service) | Unencrypted request/response exposing addresses | No | Head of Product D&I - Alex | 28.03.2024 | Security | High | Mitigated | TLS 1.3, | Proper validation between entity id and lean app token should be in place | Fully implemented | Low | Closed | Yes
16 | AVS (IBAN Verification Service) | Non-compliance with Lean dev portal requirements | No | Head of Product D&I - Alex | 28.03.2024 | Regulatory | Medium | Mitigated | Regular reviews against Lean portal standards | N/A | Fully implemented | Low | Closed | Yes
17 | Beneficiary Name (SAB AVS API) | Wrong beneficiary name mismatch leading to transfer issues | No | Head of Product D&I - Alex | 27.08.2024 | Data Integrity | Medium | Mitigated | Automated name verification & fallback checks Input validation should be in place for IBAN parameter | N/A | Fully implemented | Low | Closed | Yes
18 | Beneficiary Name (SAB AVS API) | Compromised tokens allowing unauthorized API calls | No | Head of Product D&I - Alex | 27.08.2024 | Security | High | Mitigated | Frequent token rotation | IP-based restrictions | Fully implemented | Low | Closed | Yes
19 | Beneficiary Name (SAB AVS API) | Cross-region compliance conflict if certain data is shared | No | Chief Legal Officer | 27.08.2024 | Regulatory | High | Mitigated | Data privacy assessments when cross border processing may be requested | Host validation should be in place for api endpoint and it should be only accessible from API host | Fully implemented | Low | Closed | Yes
20 | Beneficiary Name (SAB AVS API) | Lack of monitoring for name check requests leading to failed audits | No | Head of Product D&I - Alex | 27.08.2024 | Operational | Medium | Mitigated | Error handling should be in place , error message should not revel anything sensitive in response. | API usage logging and real-time alerting | Fully implemented | Low | Closed | Yes
21 | Insights via 3rd party (Mozn) | Inaccurate risk scores from third-party algorithm | No | Head of Product D&I - Alex | 06.02.2024 | Data Integrity | Medium | Mitigated | Regular calibration checks, SLA on data quality | N/A | Fully implemented | Low | Closed | Yes
22 | Insights via 3rd party (Mozn) | Data leakage if sensitive PII is shared with the 3rd party | No | Chief Legal Officer | 06.02.2024 | Security | High | Mitigated | Encrypted transfers, restricted data fields | Role based access control | Fully implemented | Low | Closed | Yes
23 | Payout - Making Payments to End-Customers | Misconfigured payout instructions leading to funds sent to wrong accounts | No | Head of Products Payments - Kunal | 23.12.2024 | Operational | High | Mitigated | Dual authorization on payouts, IBAN validation | Authentication & Authorization (role based access controls, least privilege, object level authorization) | Fully implemented | Low | Closed | Yes
24 | Payout - Making Payments to End-Customers | Fraudulent payout requests exploiting system vulnerabilities | No | Head of Products Payments - Kunal | 23.12.2024 | Security | High | Mitigated | Transaction monitoring, anomaly detection rules Confidentiality requirements (Encryption in transit and encryption at rest, anonymization of sensitive data in logs) | Integrity requirement (Input validation) | Fully implemented | Low | Closed | Yes
25 | Refunds | Duplicate or incorrect refund amounts | No | Head of Products Payments - Kunal | 19.11.2024 | Business/Process | Medium | Mitigated | Automated checks, mandatory sign-off for large refunds | Rate limiting should be in place at service level for POST /api/v1/payments/<payment_id>/refunds endpoint in order to prevent many security issues such as creation of multiple beneficiaries under same customer id , or payment id | Fully implemented | Low | Closed | Yes
26 | Refunds | Refund policy compliance failure (e.g. cross-border transactions) | No | Chief Legal Officer | 19.11.2024 | Regulatory | Medium | Mitigated | Legal review of refund flows, periodic audits Only allowed user roles should be able to perform this tasks such as Admin , Finance , Owner role etc for other user roles this functionality should not be visible . | N/A | Fully implemented | Low | Closed | Yes
27 | Payment Status Tracking | Delayed status updates creating confusion for customers | No | Head of Products Payments - Kunal | 06.09.2024 | Operational | Medium | Mitigated | Polling and push notifications, clear SLAs | N/A | Fully implemented | Low | Closed | Yes
28 | Payment Status Tracking | Incorrect post-initiation status leading to inconsistent records | No | Head of Products Payments - Kunal | 06.09.2024 | Data Integrity | High | Mitigated | Transaction logs cross-verification, real-time conflict resolution | Object Level authorization rules are in place (e.g. an entity ID is tied to a user ID which is tied to lean app token) | Fully implemented | Low | Closed | Yes
29 | Internal Billing Service | Overbilling or missed invoicing for partners | No | Head of Products Payments - Kunal | 28.01.2024 | Business/Process | Medium | Mitigated | Automated reconciliation scripts and monthly audit In case of data export from the tool only finance team should do it because it contains sensitive information about billing and data sharing about billing should follow best security practices such as sharing over one password with password protected zip file . | N/A | Fully implemented | Low | Closed | Yes
30 | Internal Billing Service | Unauthorized adjustments to billing rates or discount structures | No | Head of Products Payments - Kunal | 28.01.2024 | Security | High | Mitigated | Role-based authorizations, audit trail on billing changes All of the endpoints will be secured using JWT tokens issued by our internal oauth service.: Backend validation should be in place for auth header which means in case of header modification or removal it should result into an 401 unauthorized error message | Input validation and sanitization should be in place for all user input fields to avoid Owasp top 10 vulnerabilities | Fully implemented | Low | Closed | Yes
31 | Payout service : Dashboard Payouts Initiation | Unauthorized Approval of payment by incorrect user role | No | Head of Products Payments - Kunal | 04.03.2025 | Security | High | Mitigated | Role-based authorizations for maker and checker role | Proper JWT token validation, Feature flag in place , Privilage esclation related checks | Fully implemented | Low | Closed | Yes
32 | Subdomain takeover due to misconfigured domain | Unauthorized Access of Lean subdomains | No | Head of Devops - Illia | 04.03.2025 | Security | High | Mitigated | Attack surface monitoring in place which is integrated with slack channel | Attack surface monitoring in place which is integrated with slack channel | Fully implemented | Low | Closed | Yes
33 | AVS - self serve | If AVS will be widely available, competitors or unqualified users such could sign up, such as individuals with access to test real data | No | Head of Product D&I - Alex | 10.03.2025 | Security | High | Mitigated | If abuse is detected, shift to invite-only mode. | Ensure only AVS APIs are available , by restricting the JWT claims | Not started | Low | Open | Yes
34 | AVS - self serve | Users could repeatedly sign up under different emails to extend free access. |  | Head of Product D&I - Alex | 10.03.2025 | Commercial | High | Mitigated | Identify sign ups with the same company domain and manual checks where necessary. | Invite-only mode should be enforced by default | Not started | Low | Open | Yes
35 | AVS - self serve | Potential that a non-SAMA regulated company could sign up to Lean and use AVS, would need to be reviewed by Compliance |  | Chief Legal Officer | 10.03.2025 | Compliance | High | Mitigated | If required to only enable for SAMA regulated companies we will shift to invite-only mode. | Invite-only mode should be enforced by default | Not started | Low | open | Yes

## Security Controls List
Policies for information security
Review of the policies for information security
Information security roles and responsibilities
Segregation of duties
Contact with authorities
Contact with special interest groups
Information security in project management
Mobile device policy
Teleworking
Screening
Terms and conditions of employment
Management responsibilities
Information security awareness, education and training
Disciplinary process
Termination or change of employment responsibilities
Inventory of assets
Ownership of assets
Acceptable use of assets
Return of assets
Classification of information
Labelling of information
Handling of assets
Management of removable media
Disposal of media
Physical media transfer
Access control policy
Access to networks and network services
User registration and de-registration
User access provisioning
Management of privileged access rights
Management of secret authentication information of users
Review of user access rights
Removal or adjustment of access rights
Use of secret authentication information
Information access restriction
Secure log-on procedures
Password management system
Use of privileged utility programs
Access control to program source code
Policy on the use of cryptographic controls
Key management
Physical security perimeter
Physical entry controls
Securing offices, rooms and facilities
Protecting against external and environmental threats
Working in secure areas
Delivery and loading areas
Equipment siting and protection
Supporting utilities
Cabling security
Equipment maintenance
Removal of assets
Security of equipment and assets off-premises
Secure disposal or re-use of equipment
Unattended user equipment
Clear desk and clear screen policy
Documented operating procedures
Change management
Capacity management
Separation of development, test and operational facilities
Controls against malware
Information back-up
Event logging
Protection of log information
Administrator and operator logs
Clock synchronization
Installation of software on operational systems
Management of technical vulnerabilities
Restrictions on software installations
Information system audit controls
Network controls
Security of network services
Segregation in networks
Information transfer policies and procedures
Agreements on information transfer
Electronic messaging
Confidentiality or non-disclosure agreements
Information security requirements analysis and specification
Securing application services on public networks
Protecting application services transactions
Secure development policy
System change control procedures
Technical review of applications after operating system platform changes
Restrictions on changes to software packages
Secure system engineering principles
Secure development environment
Outsourced development
System security testing
System acceptance testing
Protection of test data
Information security policy for supplier relationships
Addressing security in supplier agreements
Information and communication technology supply chain
Monitoring and review of supplier services
Managing changes to supplier services
Responsibilities and procedures
Reporting information security events
Reporting security weaknesses
Assessment and decision of information security events
Response to information security incidents
Learning from information security incidents
Collection of evidence
Planning information security continuity
Implementing information security continuity
Verify, review and evaluate information security continuity
Availability of information processing facilities
Independent review of information security
Compliance with security policies and standards
Protection of records
Privacy and protection of personal identifiable information
Regulation of cryptographic controls
Independent review of information security
Compliance with security policies and standards
Technical compliance review
Defines security principles and guidelines to protect information assets.
Ensures security policies are updated periodically and aligned with regulations.
Defines security roles, responsibilities, and accountability across teams.
Prevents conflicts of interest by limiting access based on job roles.
Establishes communication channels with regulatory bodies for compliance.
Participation in cybersecurity forums and intelligence sharing communities.
Ensures security requirements are included from project initiation.
Defines security measures for mobile devices accessing corporate resources.
Establishes security controls for remote work environments.
Background verification of employees handling sensitive data.
Incorporates security obligations into employment contracts.
Defines executive responsibilities in security risk management.
Provides periodic training on phishing, social engineering, and compliance.
Defines consequences for violating security policies.
Ensures access is revoked promptly when employees leave or change roles.
Maintains a comprehensive list of IT assets for tracking and risk assessment.
Defines accountability for managing IT assets securely.
Defines acceptable and prohibited uses of IT resources.
Ensures return of company assets upon termination or role change.
Categorizes data based on sensitivity and regulatory requirements.
Ensures classified data is properly labeled (e.g., Confidential, Internal).
Defines protocols for managing and transferring sensitive data.
Restricts and monitors USB, external hard drives, and removable storage.
Ensures secure destruction of obsolete storage devices to prevent data leaks.
Defines security boundaries for data centers and restricted areas.
Enforces biometric or badge-based access restrictions to sensitive locations.
Protects physical workspaces from unauthorized access.
Mitigates risks from fire, floods, and power failures.
Restricts unauthorized personnel from entering critical zones.
Monitors external deliveries to prevent unauthorized access.
Defines user authentication and authorization mechanisms.
Restricts access to network resources based on need-to-know.
Manages user account provisioning and de-provisioning processes.
Implements least privilege access for system administrators.
Requires multi-factor authentication for accessing sensitive systems.
Periodically reviews and revokes unnecessary access privileges.
Enforces password complexity, expiration, and storage policies.
Restricts execution of administrative tools to authorized users.
Limits access to critical application source code repositories.
Defines encryption standards for data at rest and in transit.
Manages lifecycle of encryption keys to prevent unauthorized decryption.
Implements network firewalls, segmentation, and monitoring.
Monitors network traffic for malicious activities.
Collects security logs and alerts for anomaly detection.
Defines procedures for detecting, reporting, and responding to security incidents.
Monitors external threats and vulnerabilities affecting the organization.
Assesses security posture of third-party service providers.
Identifies and remediates software vulnerabilities.
Defines update cycles for security patches on systems and applications.
Monitors and responds to endpoint-based threats.
Centralizes log collection and real-time alerting.
Deploys antivirus and anti-malware solutions on endpoints.
Prevents unauthorized data transfers and exfiltration.
Ensures critical data and applications can be restored after an incident.
Conducts periodic disaster recovery and business continuity tests.
Defines secure coding practices for API authentication and access control.
Prevents injection attacks and input manipulation.
Mitigates DDoS attacks and abuse of services.
Restricts access based on geographic location.
Replaces sensitive data with anonymized tokens.
Integrates security checks into CI/CD pipelines.
Requires external audits and penetration testing of vendors.
Ensures TLS 1.3 and AES-256 encryption for data protection.
Grants access based on predefined roles and responsibilities.
Uses AI-driven monitoring for fraud and attack detection.
Validates consistency of stored data.
Ensures compliance with GDPR, DORA, UAE NESA, and other frameworks.
Verifies vendors comply with contractual security obligations.
Requires annual security training and phishing simulations.
Quarterly audits of privileged and sensitive accounts.
Validation between customer id, report id and lean app token should be in place so that one TPP cannot fetch reports for someone else
Versioning strategy and link expiration policies
Host validation should be in place for all new endpoints, if it is intended to be used on API host then other hosts should not be allowed to make requests to those endpoints
MFA on user login
Automated data checks and audit logs
Error handling in place which means during error messages do not reveal any sensitive information
Real-time validation and cross-source reconciliation
Confidentiality requirements (Encryption in transit and encryption at rest, anonymization of sensitive data in logs)
RBAC (Role-Based Access Control) and encryption at rest
Authentication & Authorization (role-based access controls, least privilege, object-level authorization)
Regular compliance audits, legal sign-off for new markets
Scheduled ETL runs with error-handling & backup processes
Respond with generic error messages and representative HTTP return code - avoid revealing details of the failure unnecessarily
Encryption at rest, strict data retention policies
Host validation should be in place (only API host should be able to make requests to these endpoints)
Scoring model validations and workflow approvals
Do not store PII data in any logs for this service such as Kibana
Tokenization, randomization of PII fields
Do not store PII data in any logs for this service such as Kibana
Load balancing, autoscaling triggers
SLA-based failover to secondary provider
Perform input validation for all headers and params
Perform host validation for the new API
Frequent syncs and periodic data quality checks
TLS 1.3, Proper validation between entity id and lean app token should be in place
Regular reviews against Lean portal standards
Automated name verification & fallback checks
Input validation should be in place for IBAN parameter
Frequent token rotation & IP-based restrictions
Geo-fencing, local data processing only
Host validation should be in place for API endpoint and it should be only accessible from API host
API usage logging and real-time alerting
Error handling should be in place, error messages should not reveal anything sensitive in response
Regular calibration checks, SLA on data quality
Encrypted transfers, restricted data fields
Role-based access control
Dual authorization on payouts, IBAN validation
Authentication & Authorization (role-based access controls, least privilege, object-level authorization)
Transaction monitoring, anomaly detection rules
Confidentiality requirements (Encryption in transit and encryption at rest, anonymization of sensitive data in logs)
Integrity requirement (Input validation)
Automated checks, mandatory sign-off for large refunds
Rate limiting should be in place at service level for POST /api/v1/payments/<payment_id>/refunds endpoint in order to prevent many security issues such as creation of multiple beneficiaries under same customer id, or payment id
Legal review of refund flows, periodic audits
Only allowed user roles should be able to perform these tasks such as Admin, Finance, Owner role etc. For other user roles this functionality should not be visible
Polling and push notifications, clear SLAs
Transaction logs cross-verification, real-time conflict resolution
Object Level authorization rules are in place (e.g. an entity ID is tied to a user ID which is tied to lean app token)
Automated reconciliation scripts and monthly audit
In case of data export from the tool only finance team should do it because it contains sensitive information about billing and data sharing about billing should follow best security practices such as sharing over OnePassword with password-protected zip file
Role-based authorizations, audit trail on billing changes
All of the endpoints will be secured using JWT tokens issued by our internal OAuth service
Backend validation should be in place for auth header which means in case of header modification or removal it should result in a 401 unauthorized error message
Input validation and sanitization should be in place for all user input fields to avoid OWASP Top 10 vulnerabilities

## Assets
Criticality
Asset Name | Asset Type | Example assets | Confidentiality | Integrity | Availability | Overall Criticality | Asset Owner | Role | Asset Owner Secondry | Role | Comments
Premises | Building | Premises, reception, fixture & fittings, alarms, CCTV, data processing areas, Main offices, dev centres, sales offices. | Low | Low | High | High | wafa.alamri@leantech.me | Office Manager KSA | aditya@leantech.me | CPO | Office Manager responsible for London office
Backups | Hardware | Backups of company held information (tapes, discs, server etc) | High | High | High | High | ashu@leantech.me | CTO | damian@leantech.me DevOps Team | IT Manager DEvOps
Personal Computing equipment | Hardware | All standard laptop / desktop workstations | High | Low | Medium | High | ashu@leantech.me | CTO | damian@leantech.me | IT Manager
Mobile Devices | Hardware | All mobile communication devices tablets, phones etc | Medium | Low | Low | Medium | ashu@leantech.me | CTO | aditya@leantech.me | CPO
Removable Media | Hardware | USB, CDs & DVDs | High | Low | Low | High | ashu@leantech.me | CTO | damianr@leantech.me | IT Manager
Network Infrastructure | Hardware - Business Critical | Servers, Network Infrastructure etc including Production, Development systems (within co-location data centers) (Compute) | Critical | Low | Critical | Critical | oscar@leantech.me | Devops | illia.shpak@leantech.me | DevOps
Client data | Information | Client Data (including Client provided info), Incidents and personal data - covering B2B, KYC | Critical | Critical | High | Critical | ashu@leantech.me | CTO | aditya@leantech.me | CPO
End-user data | Information | Personal data collected by client end users (financial information, no email addresses currently collected) | Critical | Critical | High | Critical | ashu@leantech.me | CTO | aditya@leantech.me | CPO
Financial data | Information | Company Accounts (Financials), Billing/Invoicing | Critical | Critical | High | Critical | aditya@leantech.me | CPO | Harryt@leantech.me | Head of Finance
Personal Data | Information | Staff Data, NI Number, Bank Details, Personnel records, Payroll, Expenses | Critical | Critical | High | Critical | Hisham@leantech.me | CEO | wendy@leantech.me | People Lead
Websites | Information | Company owned/leased websites (including Intranet; public sites) | Medium | Low | Medium | Medium | ashu@leantech.me | CTO | aditya@leantech.me | CPO
Reputation | Intangiable | Company Reputation | Critical | Critical | Critical | Critical | Hisham@leantech.me | CEO | Ashu@leantech.me | CTO
Employees | People | Company Staff (Directors, Supervisors, Operational staff, HR), | High | High | High | High | aditya@leantech.me | CPO | Wendy@leantech.me Marie@leantech.me | People Lead General Counsel
Third Parties | Services | Contractual obligations; contracts & SLAs; managed office providers, landlords cleaners, suppliers, etc | High | High | Medium | High | aditya@leantech.me | CPO | Marie@leantech.me hisham@leantech.me | General Counsel CEO
Software & Development | Software and Microservices | Software employed in the business including bespoke software and application software. Software Development - Internal SDLC | Critical | Critical | Critical | Critical | ashu@leantech.me | CTO | dragos@leantech.me | Head of Infosec